## ecen-361 maze-solving
ECEN-361 Maze-solving Robot
Main
Name | Person | Status | Date
Purchase RC car found on Amazon |  | Done | 2024-02-03
Ensure we can access the sensory data on the RC car |  | Done | 2024-02-17
Check if a compass or some kind of directional module is built-in to the kit; if not, find an Arduino compass module and purchase it |  | Done | 2024-03-02
Learn how the included code interacts with the RC car |  | Done | 2024-02-24
Begin writing mapping software |  | Done | 2024-02-24
Find exactly how to access the ultrasonic sensor data |  | Done | 2024-02-24
Learn how to change acceleration and direction of the car |  | Done | 2024-02-24
Find where the entry point of the program is |  | Done | 2024-02-24
Make logic table for the robot's navigation |  | Done | 2024-03-09
Learn how to balance the car using the gyroscope |  | Done | 2024-03-09
Learn how to make the car turn exactly a number of degrees |  | Done | 2024-03-16
Make a first draft of navigation algorithm |  | Working on it | 2024-03-16
Get cardboard for maze |  | Working on it | 2024-03-20
Construct maze and test navigation algorithm |  | Working on it | 2024-03-23
Debug navigation algorithm |  | Working on it | 2024-03-30
Rewrite code which receives data in |  | Working on it | 2024-03-30
2024-02-03 to 2024-03-30